Template A: Simple Plush (Fastest Path) — Editable Gantt Template

Simple designs move fastest when materials and approvals don’t drift.

Use this template for simple custom plush designs with standard fabrics, minimal accessories, and straightforward embroidery. It fits pilot programs and fast launches because sampling risk is low and production lead time is easier to stabilize.

Project Inputs (Fill In)

| Target arrival date (warehouse/3PL/FBA) |  |
| --- | --- |
| Destination type (3PL / retail DC / e-commerce) |  |
| Shipping method (air / sea / express / split) |  |
| Incoterms (FOB / FCA / CIF / DAP / DDP etc.) |  |
| SKU count (single SKU preferred) |  |
| Decision owner (who approves each round) |  |

Best For

Standard fabric + simple embroidery

No magnets/electronics

Low accessory complexity (single SKU preferred)

Gantt Blocks (Week-Based)

| Block | Start Week | End Week | Notes / What to Lock |
| --- | --- | --- | --- |
| Feasibility + quote + file check + scope lock | 0 | 0 | Lock target feel/fabric direction, size, logo placement, label rules |
| Sampling Round 1 | 1 | 2 | One consolidated feedback list; measurable review points |
| Revisions (if needed) + approval | 3 | 3 | Confirm change list; approve against one baseline |
| Production lead time | 4 | 6 | No spec resets; keep must-not-change items locked |
| QC + packing readiness | 6 | 7 | Confirm carton rules, pack-out checks, receiving requirements |
| Shipping docs + booking cut-offs | 6 | 7 | Prepare CI/PL/carton marks drafts; confirm consignee/notify party |
| Transit (depends on method) | 7 | — | Choose shipping method early; plan buffer based on transit mode |

Key Inputs to Lock Early

Target feel and fabric direction (pile direction / sheen behavior)

Size and key measurements (add tolerance where needed)

Logo/patch/label placement anchors (measurable reference points)

Label rules (market/channel requirements, languages, barcode/SKU placement)

Note: Templates help you plan realistically; lead time still depends on complexity, revision rounds, and shipping method.