Template B: Standard Brand Plush (Most Common) — Editable Gantt Template

This is the most common path for retail and e-commerce brands.

Use this template for typical brand plush programs with multiple colors/variants, mixed decoration (embroidery + patch/print), packaging labels/carton marks, and 1–2 sampling rounds. It is the most realistic template for clean approvals and repeatable reorders.

Project Inputs (Fill In)

| Target arrival date (warehouse/3PL/FBA) |  |
| --- | --- |
| Destination type (3PL / retail DC / e-commerce) |  |
| Shipping method (air / sea / express / split) |  |
| Incoterms (FOB / FCA / CIF / DAP / DDP etc.) |  |
| SKU count + variant notes (colors/sizes) |  |
| Decoration plan (embroidery / patch / print) + placement notes |  |
| Packaging labels required (barcode/SKU, warning text, languages) |  |
| Carton marks template + mixed-SKU carton rules (allowed or not) |  |

Best For

Multiple colors/variants (SKU control matters)

Embroidery + patch/print mix

Standard accessories (keychain, zipper, etc.)

Packaging labels + carton marks required

Gantt Blocks (Week-Based)

| Block | Start Week | End Week | Notes / What to Lock |
| --- | --- | --- | --- |
| Feasibility + spec alignment (SKU + pack-out rules) | 0 | 0 | Lock SKU list, packaging/label rules, carton marks format, destination receiving requirements |
| Sampling Round 1 | 1 | 2 | Confirm structure/appearance baseline; collect consolidated feedback list |
| Sampling Round 2 + approval (golden sample lock) | 3 | 4 | Lock fabric/decoration methods, placement anchors, and golden reference approval standard |
| Production lead time | 5 | 9 | Keep must-not-change items locked; control variant changeovers to protect efficiency |
| QC + packing + carton marks lock | 9 | 10 | Finalize carton marks, mixed-SKU packing rules, and packing verification checklist |
| Shipping docs + booking cut-offs | 9 | 10 | Prepare CI/PL/carton data drafts; confirm consignee/notify party; send packing data to forwarder |
| Transit (depends on method) | 10 | — | Choose method early; plan buffer based on transit mode and delivery appointments |

Key Inputs to Lock Early (To Protect Approvals + Reorders)

SKU list and variant rules (what changes vs what stays identical)

Fabric/hand-feel direction and color reference standard

Decoration method split (what is embroidered vs printed vs patched)

Placement anchors for logo/labels (measurable reference points)

Packaging label requirements (barcode, warning text, language versions)

Carton marks format and mixed-SKU carton rules

Note: Templates help you plan realistically; lead time still depends on complexity, revision rounds, and shipping method.