Template C: Complex / High-Risk Plush — Editable Gantt Template

Complexity adds checkpoints—plan extra sampling and parallel testing.

Use this template when you have magnets/electronics, complex attachments, special prints/coatings, strict market/channel requirements, or multiple approvers. Plan more sampling time, lock final spec earlier, and allocate buffer for testing and documentation—ideally running testing in parallel where possible.

Project Inputs (Fill In)

| Target arrival date (warehouse/3PL/retail DC/FBA) |  |
| --- | --- |
| Destination type + channel requirements (retail / e-commerce / licensed) |  |
| Shipping method (air / sea / express / split) |  |
| Incoterms (FOB / FCA / CIF / DAP / DDP etc.) |  |
| SKU count + variant notes (colors/sizes) |  |
| Components list (magnets/electronics/mechanisms) |  |
| Decoration plan (printing/coatings/embroidery/patch) + placement notes |  |
| Age grade + labeling rules (languages, warnings, barcode/SKU placement) |  |
| Compliance/testing scope (market + required standards + nominated lab if any) |  |
| Approver list + decision owner (who signs off each round) |  |

Best For

Magnets / electronics / special mechanisms

High-detail printing or coatings

Strict retailer/market compliance processes

Many stakeholders approving samples

Gantt Blocks (Week-Based)

| Block | Start Week | End Week | Notes / What to Lock |
| --- | --- | --- | --- |
| Feasibility + risk review + scope lock | 0 | 1 | Lock scope, components list, age grade direction, and compliance path; identify high-risk points early |
| Sampling Round 1 | 2 | 3 | Validate structure + integration feasibility; collect consolidated feedback list |
| Sampling Round 2 | 4 | 5 | Refine decoration/attachments; confirm repeatability and safety-critical details |
| Pre-production approval (golden sample lock) | 6 | 6 | Lock final spec and golden reference standard before bulk and before final testing submission |
| Production lead time | 7 | 12 | Maintain strict change control; avoid component substitutions; protect repeatability |
| QC + packing readiness | 12 | 13 | Confirm packing readiness, receiving rules, and inspection evidence plan |
| Shipping docs + booking cut-offs | 12 | 13 | Prepare CI/PL/carton data drafts; confirm consignee/notify party; coordinate with broker/forwarder |
| Transit (depends on method) | 13 | — | Choose method early; keep buffer for appointments and release workflow |
| Optional (parallel): Testing workflow planning | 2 | 6 | Run planning in parallel: lab booking, scope alignment, and submission requirements to reduce idle time |

Critical Must-Not-Change Items Before Any Testing Submission

Fabric type (pile height/texture and final intent)

Decoration method (printing/coatings/embroidery/patch split)

Components list (magnets/electronics/mechanisms)

Age grade + labeling rules (warnings, languages, SKU/barcode placement)

Note: Templates help you plan realistically; lead time still depends on complexity, revision rounds, and shipping method.